## Index
Autonomous Robot Project - Session Tracker
Voice-Controlled Learning Robot ¦ Budget: $2,000 ¦ Open Source Only
Last Updated: December 21, 2025
Phase 0 Status: COMPLETE ✅
Budget: $1,910.54 / $2,000 (95.5%)
Remaining: $89.46
Quick Stats:
• Total Sessions: 7
• Time Invested: ~20 hours
• Hardware Components: 15+
• Major Orders: 3 (all placed Dec 21)
• Next Milestone: Printer arrives Dec 24
Session Overview
# | Date | Duration | Phase | Focus | Spent | Total | Status | Sheet
1-5 | Nov-Dec | ~12h | Planning | Research, parts selection | $462 | $462 | ✅ | → Sessions_1-6
6 | Dec 20 | 2.5h | Phase 0 | OS install, validation | $0 | $462 | ✅ | → Sessions_1-6
7 | Dec 21 | 3h | Phase 0 | Camera, printer, orders | $1,448 | $1,910 | ✅ | → 2025-12-21_18-45
Hardware Procurement Status
Order #111-1218755-5033819 (Amazon): | CORE One Printer - $1,218.43 | Arrives Dec 24 🎄
Order #GE108674O7805NL (Prusa): | 4kg Filament (rPLA+rPETG) - $140.11 | Arrives Dec 25-26 🎅
Order #111-5198911-0120202 (Amazon): | Hardware/Tools (5 items) - $90.00 | Arrives Dec 22-30
Next Milestones
Dec 22: | First tools arrive (calipers, cutters, deburring)
Dec 24: | CORE One printer arrives
Dec 25: | 8-hour printer assembly + filament arrives
Dec 26: | First test prints
Jan 6-12: | Chassis CAD design
Jan 13-19: | Print final chassis in rPETG
Late Jan: | Phase 1 - Motors & wheels

## Sessions_1-6
Sessions 1-6: Project Foundation & Phase 0 Setup
November - December 20, 2024 ¦ Duration: ~15 hours total
Overview
These sessions established the project foundation, selected all hardware components,
validated the Raspberry Pi 5, and prepared the system for camera integration.
Key Accomplishments (Sessions 1-5: Planning & Procurement)
✅ Project scope defined: Autonomous robot with voice control, computer vision
✅ Hardware platform selected: Raspberry Pi 5 (8GB)
✅ Vision system designed: Dual Camera Module 3 Wide (120° FOV, stereo vision)
✅ Sensors selected: 3× HC-SR04 ultrasonic (obstacle detection)
✅ Power system: Anker PowerCore 20K (26,800mAh battery)
✅ Development tools: Klein MM420 multimeter for validation
✅ Storage: SanDisk Extreme 64GB microSD (A2 rated)
✅ All Phase 0 hardware ordered and delivered by Dec 13
✅ Budget strategy: $2,000 total, open-source software only
✅ Development approach: Voice-controlled learning (no pre-programmed behaviors)
Session 6: OS Installation & Hardware Validation (Dec 20, 2024)
✅ Pi 5 hardware validated with multimeter (3.3V & 5V rails within spec)
✅ Raspberry Pi OS 64-bit installed (Debian Trixie base)
✅ Headless SSH configured (robot.local working via mDNS)
✅ System updates completed (37 packages upgraded)
✅ OpenCV 4.10.0 installed via apt (ARM-optimized)
✅ picamera2 0.3.33 validated (camera library ready)
✅ Network configuration resolved (WiFi + hostname discovery)
✅ Thermal baseline: 39.5°C idle (no active cooler needed yet)
Hardware Inventory (As of Session 6)
Component | Specification | Cost | Status
Raspberry Pi 5 | 8GB RAM, BCM2712 CPU | $80 | ✅ Validated
Camera Module 3 Wide (×2) | 120° FOV, 11.9MP, IMX708 | $82 | ⏳ Ready to connect
HC-SR04 Sensors (×3) | Ultrasonic, 2-400cm range | $12 | ✅ In hand
Anker PowerCore 20K | 26,800mAh, USB-C PD | $52 | ✅ Ready
Klein MM420 Multimeter | Auto-ranging, DC validation | $65 | ✅ Used
SanDisk Extreme 64GB | A2 rated, 160MB/s read | $16 | ✅ OS installed
Official USB-C Power | 27W PD adapter | $12 | ✅ Working
Breadboard & Electronics | Jumpers, logic converter | $20 | ✅ Ready
Networking | Eero mesh WiFi | $71 | ✅ Connected
Key Technical Decisions
• Headless operation: SSH only, no monitor/keyboard (authentic robot deployment)
• Package manager: apt over pip for core libraries (ARM-optimized binaries)
• Network: Manual WiFi credentials (auto-detect failed on mesh network)
• Validation: DC voltage testing before connecting peripherals (prevented damage)
• Camera: Module 3 Wide selected for 120° FOV (stereo vision baseline)
• Budget: Open-source software only, $2,000 hardware cap
Total Spending (Sessions 1-6)
Amount: $462
Budget Remaining: $1,538
Next Steps → Session 7
• Connect Camera Module 3 to Pi 5
• Test camera detection with libcamera
• Research 3D printer for chassis fabrication
• Begin Phase 0 completion (all hardware acquired)

## 2025-12-21_18-45
Session 7: Camera Setup & 3D Printer Purchase
Date: | December 21, 2025
Duration: | 3 hours
Phase: | Phase 0 - COMPLETE ✅
Focus: | Camera connection, 3D printer research/purchase, complete Phase 0 procurement
Key Accomplishments
✅ Camera Module 3 connected to Pi 5 (defective cable replaced, working)
✅ First test image captured: 4608×2592 resolution, IMX708 sensor validated
✅ CORE One 3D printer ordered ($1,218.43, Amazon, arrives Dec 24)
✅ 4kg recycled filament ordered ($140.11, Prusa Direct, arrives Dec 25-26)
✅ Hardware & tools ordered ($90.00, Amazon, arrives Dec 22-30)
✅ Sustainable materials strategy: rPETG structure + rPLA prototyping
✅ Hybrid design approach: 3D print custom + buy metal standard parts
✅ Phase 0 procurement 100% complete - all orders placed!
Technical Details
Camera Module 3 Connection:
Hardware: | Raspberry Pi Camera Module 3 Wide (120° FOV, 11.9MP, Sony IMX708)
Port: | Pi 5 DISP 1 (upper CSI connector, 22-pin)
Cable: | 22-pin to 15-pin adapter (200mm, included with camera)
Issue: | First ribbon cable defective (camera not detected)
Solution: | Swapped to second included cable - immediately detected as imx708_wide
Orientation: | Blue stripe toward Ethernet (Pi end), away from lens (camera end)
Test: | libcamera-still -o test.jpg --width 4608 --height 2592
Result: | First test image captured successfully - 11.9MP, 30fps capability
3D Printer Selection:
Selected: | Prusa CORE One Kit ($949 + tax = $1,218.43 total)
Design: | CoreXY enclosed (vs traditional bedslinger)
Speed: | 120% faster than MK4S (300mm/s vs 200mm/s)
Build Volume: | 250×220×270mm (30% larger than MK4)
Footprint: | 50% smaller desk space (CoreXY gantry efficiency)
Enclosure: | Full enclosure enables ABS/ASA/Nylon printing (future)
Why vs Bambu Lab: | Open source, serviceable, no vendor lock-in, sufficient speed
Vendor: | Amazon vs Prusa Direct (+$80 premium for 5-week time savings)
Delivery: | December 24, 2025 (vs late January from Czech Republic)
Filament Strategy:
Primary: | rPETG (recycled PETG) - 2kg for structural chassis components
Properties: | Stronger than PLA, heat resistant to 80°C, impact resistant
Cost: | ~$30/kg ($15 premium over virgin PETG)
Secondary: | rPLA (recycled PLA) - 2kg for prototyping, test fits
Properties: | Easy to print, good dimensional accuracy, lower temperature
Cost: | ~$25/kg
Sustainability: | Recycled from plastic bottles (rPETG) and PLA waste (rPLA)
Philosophy: | Design right first, use less material, make durable parts
Hardware & Tools Procured:
Hilitchi 705pc Screw Kit: | $15.99 - M3/M4/M5 stainless steel (arrives Dec 30)
INCLY Heat Set Inserts: | $8.54 - 130pc M3 brass + soldering tip (arrives Dec 28)
HARDELL Digital Calipers: | $22.99 - 6" stainless, 0.001" accuracy (arrives Dec 22)
Hakko Flush Cutters: | $20.65 - 2-pack micro cutters (arrives Dec 22)
AFA Deburring Tool: | $13.99 - Aluminum handle, 11 blades (arrives Dec 22)
Orders Placed
Order # | Vendor | Items | Total | Delivery
111-1218755-5033819 | Amazon | CORE One 3D Printer | $1,218.43 | Dec 24 🎄
GE108674O7805NL | Prusa Direct | 4kg Filament (rPLA+rPETG) | $140.11 | Dec 25-26 🎅
111-5198911-0120202 | Amazon | Hardware/Tools (5 items) | $90.00 | Dec 22-30
Key Decisions Made
• CORE One > MK4S: | 120% faster, enclosed, CoreXY design, 30% larger build, flagship model
• Amazon > Prusa Direct: | $80 premium justified by 5-week time savings (Dec 24 vs late Jan)
• Recycled materials: | rPETG for structure, rPLA for prototyping ($20 sustainability premium)
• Hybrid design: | 3D print custom geometry, buy commercial metal parts (wheels, mounts)
• Skip air filter: | $99 saved - PLA/PETG produce minimal VOCs, enclosure contains particles
• Time value: | Paying premium for immediate delivery maintains project momentum
Problems & Solutions
Problem: Camera not detected:
First ribbon cable was defective. Solution: Swapped to second included cable - worked immediately. Lesson: Always have spare cables for critical components.
Problem: Hardware ASINs out of stock:
2 of 5 planned items unavailable. Solution: Searched for current alternatives, verified each in-stock before ordering. Lesson: Product availability highly dynamic, verify current stock.
Problem: Budget exceeded initial estimate:
CORE One $150 over anticipated MK4. Solution: Justified by speed, enclosure, future-proofing. Lesson: Pay for quality on critical tools, time value matters.
Budget Tracking
Category | Amount | Notes
Prior Sessions (1-6): | $462.00 | Pi 5, cameras, sensors, power, tools, storage
CORE One Printer: | $1,218.43 | Includes $114.28 WA sales tax
Filament (4kg): | $140.11 | Includes $47.99 FedEx shipping + $13.14 tax
Hardware/Tools: | $90.00 | Includes tax on 5 items
Session 7 Total: | $1,448.54
Phase 0 Total: | $1,910.54
Original Budget: | $2,000.00
Remaining: | $89.46 | 4.5% remaining for Phase 1
Next Actions
Immediate (Dec 22-23):
• Download PrusaSlicer: https://www.prusa3d.com/page/prusaslicer_424/
• Watch CORE One assembly video (YouTube: 'Prusa CORE One assembly official')
• Clear workspace on desk (~3×3 feet for assembly)
• Organize tools for assembly
• Read assembly manual: https://help.prusa3d.com/category/core-one_1172
Assembly Day (Dec 24-25):
• Unbox CORE One carefully (photograph parts for reference)
• Inventory all components against packing list
• Follow assembly manual step-by-step (~8 hours)
• Test each subsystem during assembly
• First power-on and self-test calibration
• Load filament (sample Galaxy Black or recycled when arrives)
• First layer calibration (automatic)
• First test print (calibration cube)
Post-Assembly (Dec 26-30):
• Print temperature tower (optimize print settings for rPETG/rPLA)
• Print calibration checkerboard (for camera calibration)
• Print test chassis components (validate design workflow)
• Practice heat-set insert installation (when arrives Dec 28)
• Start chassis CAD design (measure Pi 5, cameras, battery)
Long-term (January):
• Week of Jan 6: Complete chassis CAD design in FreeCAD/Fusion 360
• Week of Jan 13: Print final chassis in rPETG with heat-set inserts
• Week of Jan 20: Assemble chassis, mount Pi 5, cameras, electronics
• Late January: Order Phase 1 components (motors, wheels, driver board)