## Index
Autonomous Robot Project - Session Tracker
Voice-Controlled Learning Robot ¦ Budget: $2,000 ¦ Open Source Only
Last Updated: December 21, 2025
Phase 0 Status: COMPLETE ✅
Budget: $1,910.54 / $2,000 (95.5%)
Remaining: $89.46
Quick Stats:
• Total Sessions: 7
• Time Invested: ~20 hours
• Hardware Components: 15+
• Major Orders: 3 (all placed Dec 21)
• Next Milestone: Printer arrives Dec 24
Session Overview
# | Date | Duration | Phase | Focus | Spent | Total | Status | Sheet
1-5 | Nov-Dec | ~12h | Planning | Research, parts selection | $462 | $462 | ✅ | → Sessions_1-6
6 | Dec 20 | 2.5h | Phase 0 | OS install, validation | $0 | $462 | ✅ | → Sessions_1-6
7 | Dec 21 | 3h | Phase 0 | Camera, printer, orders | $1,448 | $1,910 | ✅ | → 2025-12-21_18-45
Hardware Procurement Status
Order #111-1218755-5033819 (Amazon): | CORE One Printer - $1,218.43 | Arrives Dec 24 🎄
Order #GE108674O7805NL (Prusa): | 4kg Filament (rPLA+rPETG) - $140.11 | Arrives Dec 25-26 🎅
Order #111-5198911-0120202 (Amazon): | Hardware/Tools (5 items) - $90.00 | Arrives Dec 22-30
Next Milestones
Dec 22: | First tools arrive (calipers, cutters, deburring)
Dec 24: | CORE One printer arrives
Dec 25: | 8-hour printer assembly + filament arrives
Dec 26: | First test prints
Jan 6-12: | Chassis CAD design
Jan 13-19: | Print final chassis in rPETG
Late Jan: | Phase 1 - Motors & wheels

## Sessions_1-6
Sessions 1-6: Project Foundation & Phase 0 Setup
November - December 20, 2024 ¦ Duration: ~15 hours total
Overview
These sessions established the project foundation, selected all hardware components,
validated the Raspberry Pi 5, and prepared the system for camera integration.
Key Accomplishments (Sessions 1-5: Planning & Procurement)
✅ Project scope defined: Autonomous robot with voice control, computer vision
✅ Hardware platform selected: Raspberry Pi 5 (8GB)
✅ Vision system designed: Dual Camera Module 3 Wide (120° FOV, stereo vision)
✅ Sensors selected: 3× HC-SR04 ultrasonic (obstacle detection)
✅ Power system: Anker PowerCore 20K (26,800mAh battery)
✅ Development tools: Klein MM420 multimeter for validation
✅ Storage: SanDisk Extreme 64GB microSD (A2 rated)
✅ All Phase 0 hardware ordered and delivered by Dec 13
✅ Budget strategy: $2,000 total, open-source software only
✅ Development approach: Voice-controlled learning (no pre-programmed behaviors)
Session 6: OS Installation & Hardware Validation (Dec 20, 2024)
✅ Pi 5 hardware validated with multimeter (3.3V & 5V rails within spec)
✅ Raspberry Pi OS 64-bit installed (Debian Trixie base)
✅ Headless SSH configured (robot.local working via mDNS)
✅ System updates completed (37 packages upgraded)
✅ OpenCV 4.10.0 installed via apt (ARM-optimized)
✅ picamera2 0.3.33 validated (camera library ready)
✅ Network configuration resolved (WiFi + hostname discovery)
✅ Thermal baseline: 39.5°C idle (no active cooler needed yet)
Hardware Inventory (As of Session 6)
Component | Specification | Cost | Status
Raspberry Pi 5 | 8GB RAM, BCM2712 CPU | $80 | ✅ Validated
Camera Module 3 Wide (×2) | 120° FOV, 11.9MP, IMX708 | $82 | ⏳ Ready to connect
HC-SR04 Sensors (×3) | Ultrasonic, 2-400cm range | $12 | ✅ In hand
Anker PowerCore 20K | 26,800mAh, USB-C PD | $52 | ✅ Ready
Klein MM420 Multimeter | Auto-ranging, DC validation | $65 | ✅ Used
SanDisk Extreme 64GB | A2 rated, 160MB/s read | $16 | ✅ OS installed
Official USB-C Power | 27W PD adapter | $12 | ✅ Working
Breadboard & Electronics | Jumpers, logic converter | $20 | ✅ Ready
Networking | Eero mesh WiFi | $71 | ✅ Connected
Key Technical Decisions
• Headless operation: SSH only, no monitor/keyboard (authentic robot deployment)
• Package manager: apt over pip for core libraries (ARM-optimized binaries)
• Network: Manual WiFi credentials (auto-detect failed on mesh network)
• Validation: DC voltage testing before connecting peripherals (prevented damage)
• Camera: Module 3 Wide selected for 120° FOV (stereo vision baseline)
• Budget: Open-source software only, $2,000 hardware cap
Total Spending (Sessions 1-6)
Amount: $462
Budget Remaining: $1,538
Next Steps → Session 7
• Connect Camera Module 3 to Pi 5
• Test camera detection with libcamera
• Research 3D printer for chassis fabrication
• Begin Phase 0 completion (all hardware acquired)

## 2025-12-21_18-45
Session 7: Camera Setup & 3D Printer Purchase
Date: | December 21, 2025
Duration: | 3 hours
Phase: | Phase 0 - COMPLETE ✅
Focus: | Camera connection, 3D printer research/purchase, complete Phase 0 procurement
Key Accomplishments
✅ Camera Module 3 connected to Pi 5 (defective cable replaced, working)
✅ First test image captured: 4608×2592 resolution, IMX708 sensor validated
✅ CORE One 3D printer ordered ($1,218.43, Amazon, arrives Dec 24)
✅ 4kg recycled filament ordered ($140.11, Prusa Direct, arrives Dec 25-26)
✅ Hardware & tools ordered ($90.00, Amazon, arrives Dec 22-30)
✅ Sustainable materials strategy: rPETG structure + rPLA prototyping
✅ Hybrid design approach: 3D print custom + buy metal standard parts
✅ Phase 0 procurement 100% complete - all orders placed!
Technical Details
Camera Module 3 Connection:
Hardware: | Raspberry Pi Camera Module 3 Wide (120° FOV, 11.9MP, Sony IMX708)
Port: | Pi 5 DISP 1 (upper CSI connector, 22-pin)
Cable: | 22-pin to 15-pin adapter (200mm, included with camera)
Issue: | First ribbon cable defective (camera not detected)
Solution: | Swapped to second included cable - immediately detected as imx708_wide
Orientation: | Blue stripe toward Ethernet (Pi end), away from lens (camera end)
Test: | libcamera-still -o test.jpg --width 4608 --height 2592
Result: | First test image captured successfully - 11.9MP, 30fps capability
3D Printer Selection:
Selected: | Prusa CORE One Kit ($949 + tax = $1,218.43 total)
Design: | CoreXY enclosed (vs traditional bedslinger)
Speed: | 120% faster than MK4S (300mm/s vs 200mm/s)
Build Volume: | 250×220×270mm (30% larger than MK4)
Footprint: | 50% smaller desk space (CoreXY gantry efficiency)
Enclosure: | Full enclosure enables ABS/ASA/Nylon printing (future)
Why vs Bambu Lab: | Open source, serviceable, no vendor lock-in, sufficient speed
Vendor: | Amazon vs Prusa Direct (+$80 premium for 5-week time savings)
Delivery: | December 24, 2025 (vs late January from Czech Republic)
Filament Strategy:
Primary: | rPETG (recycled PETG) - 2kg for structural chassis components
Properties: | Stronger than PLA, heat resistant to 80°C, impact resistant
Cost: | ~$30/kg ($15 premium over virgin PETG)
Secondary: | rPLA (recycled PLA) - 2kg for prototyping, test fits
Properties: | Easy to print, good dimensional accuracy, lower temperature
Cost: | ~$25/kg
Sustainability: | Recycled from plastic bottles (rPETG) and PLA waste (rPLA)
Philosophy: | Design right first, use less material, make durable parts
Hardware & Tools Procured:
Hilitchi 705pc Screw Kit: | $15.99 - M3/M4/M5 stainless steel (arrives Dec 30)
INCLY Heat Set Inserts: | $8.54 - 130pc M3 brass + soldering tip (arrives Dec 28)
HARDELL Digital Calipers: | $22.99 - 6" stainless, 0.001" accuracy (arrives Dec 22)
Hakko Flush Cutters: | $20.65 - 2-pack micro cutters (arrives Dec 22)
AFA Deburring Tool: | $13.99 - Aluminum handle, 11 blades (arrives Dec 22)
Orders Placed
Order # | Vendor | Items | Total | Delivery
111-1218755-5033819 | Amazon | CORE One 3D Printer | $1,218.43 | Dec 24 🎄
GE108674O7805NL | Prusa Direct | 4kg Filament (rPLA+rPETG) | $140.11 | Dec 25-26 🎅
111-5198911-0120202 | Amazon | Hardware/Tools (5 items) | $90.00 | Dec 22-30
Key Decisions Made
• CORE One > MK4S: | 120% faster, enclosed, CoreXY design, 30% larger build, flagship model
• Amazon > Prusa Direct: | $80 premium justified by 5-week time savings (Dec 24 vs late Jan)
• Recycled materials: | rPETG for structure, rPLA for prototyping ($20 sustainability premium)
• Hybrid design: | 3D print custom geometry, buy commercial metal parts (wheels, mounts)
• Skip air filter: | $99 saved - PLA/PETG produce minimal VOCs, enclosure contains particles
• Time value: | Paying premium for immediate delivery maintains project momentum
Problems & Solutions
Problem: Camera not detected:
First ribbon cable was defective. Solution: Swapped to second included cable - worked immediately. Lesson: Always have spare cables for critical components.
Problem: Hardware ASINs out of stock:
2 of 5 planned items unavailable. Solution: Searched for current alternatives, verified each in-stock before ordering. Lesson: Product availability highly dynamic, verify current stock.
Problem: Budget exceeded initial estimate:
CORE One $150 over anticipated MK4. Solution: Justified by speed, enclosure, future-proofing. Lesson: Pay for quality on critical tools, time value matters.
Budget Tracking
Category | Amount | Notes
Prior Sessions (1-6): | $462.00 | Pi 5, cameras, sensors, power, tools, storage
CORE One Printer: | $1,218.43 | Includes $114.28 WA sales tax
Filament (4kg): | $140.11 | Includes $47.99 FedEx shipping + $13.14 tax
Hardware/Tools: | $90.00 | Includes tax on 5 items
Session 7 Total: | $1,448.54
Phase 0 Total: | $1,910.54
Original Budget: | $2,000.00
Remaining: | $89.46 | 4.5% remaining for Phase 1
Next Actions
Immediate (Dec 22-23):
• Download PrusaSlicer: https://www.prusa3d.com/page/prusaslicer_424/
• Watch CORE One assembly video (YouTube: 'Prusa CORE One assembly official')
• Clear workspace on desk (~3×3 feet for assembly)
• Organize tools for assembly
• Read assembly manual: https://help.prusa3d.com/category/core-one_1172
Assembly Day (Dec 24-25):
• Unbox CORE One carefully (photograph parts for reference)
• Inventory all components against packing list
• Follow assembly manual step-by-step (~8 hours)
• Test each subsystem during assembly
• First power-on and self-test calibration
• Load filament (sample Galaxy Black or recycled when arrives)
• First layer calibration (automatic)
• First test print (calibration cube)
Post-Assembly (Dec 26-30):
• Print temperature tower (optimize print settings for rPETG/rPLA)
• Print calibration checkerboard (for camera calibration)
• Print test chassis components (validate design workflow)
• Practice heat-set insert installation (when arrives Dec 28)
• Start chassis CAD design (measure Pi 5, cameras, battery)
Long-term (January):
• Week of Jan 6: Complete chassis CAD design in FreeCAD/Fusion 360
• Week of Jan 13: Print final chassis in rPETG with heat-set inserts
• Week of Jan 20: Assemble chassis, mount Pi 5, cameras, electronics
• Late January: Order Phase 1 components (motors, wheels, driver board)

## 2026-01-25_OpenSCAD
Session: OpenSCAD Setup & Project Reorganization
January 25, 2026 ¦ Duration: ~4 hours
Overview
Established OpenSCAD development environment, learned CAD design fundamentals for robot chassis development, and reorganized project structure from numbered lessons to topic-based learning directories. Created tutorial progression for 3D design of interlocking robot parts.
Key Accomplishments
✅ OpenSCAD installed on Windows (latest version 2024.11.12)
✅ VS Code OpenSCAD extension configured with auto-update
✅ Dual-screen workflow established (VS Code editing ¦ OpenSCAD preview)
✅ OpenSCAD fundamentals learned: cylinders, cubes, difference operations
✅ Critical concept: clearance tolerances for sliding fits (0.3mm standard)
✅ Peg-in-hole design mastered with proper dimensional accuracy
✅ Understanding of $fn parameter for curve smoothness (60-80 design, 100 export)
✅ Print tolerance concepts: design clearance vs printer accuracy
✅ Project reorganized from src/learning/01-07_topics to topic-based structure
✅ Created learning/ with computer_vision, openscad, machine_learning, etc.
✅ Expanded hardware/ with chassis, camera, sensors, legs, library subdirs
✅ PowerShell migration script created with comprehensive logging
✅ Successfully migrated 17 files with git mv (preserved history)
✅ Created maintenance/ folder for project management scripts
✅ Tutorial files organized: learning/openscad/basics/
Technical Details
OpenSCAD Workflow: Edit .scad files in VS Code → Auto-preview in OpenSCAD app → Export STL → PrusaSlicer
File Resolution: $fn=60-80 for design preview (fast), $fn=100 for final STL export (smooth)
Clearance Standards: Press fit (0.05-0.1mm), Sliding fit (0.2-0.3mm), Loose fit (0.4-0.5mm)
Printer Tolerance: Prusa CORE One ~±0.1-0.2mm XY accuracy (fixed), 0.05-0.3mm layer height (controllable)
Project Structure: learning/ (experiments), src/ (production code), hardware/ (final CAD)
Git Workflow: Used 'git mv' to preserve file history during reorganization
Migration Stats: 20 new directories created, 17 files moved, 0 failures
Files Created
learning/openscad/basics/01_cylinder.scad - Basic shapes introduction
learning/openscad/basics/02_cube_with_holes.scad - Difference operations for mounting holes
learning/openscad/basics/03_wheel.scad - Parametric wheel with weight reduction
learning/openscad/basics/peg_in_hole_example.scad - Interlocking parts with clearance
maintenance/reorganize_folders_1-24-26.ps1 - PowerShell migration script
maintenance/reorganize_log_20260125_052929.txt - Migration execution log
learning_new/ - Complete topic-based directory structure (20 subdirectories)
hardware/chassis, camera, sensors, legs, library, electronics/ - Expanded structure
Next Steps
🔄 Finalize directory reorganization (rename learning_new to learning, remove old structure)
🔄 Commit reorganization to Git with detailed commit message
🔄 Start designing actual robot parts (motor mount, camera bracket, sensor mounts)
🔄 Download Spot Micro STL files for quadruped reference
🔄 Calculate optimal stereo camera baseline spacing (10-20cm range)
🔄 Create parametric chassis base plate in OpenSCAD
🔄 Design wheel motor brackets for Phase 1 wheeled base
🔄 Test print tolerance calibration pieces on Prusa CORE One
Key Learnings
OpenSCAD is code-based CAD - perfect for parametric robot design and version control
Clearance is NOT printer error compensation - it's intentional design gap for part fit
$fn affects visual smoothness only - dimensional accuracy comes from proper measurements
Topic-based organization scales better than numbered lessons for multi-year projects
Git mv preserves file history during reorganization (critical for long-term tracking)
Test prints are essential - design clearance values need real-world validation
Spot Micro chassis can be used with wheels first, then retrofit legs later (hybrid approach)

## 2026-01-26_Chassis-Design
ROBOT PROJECT SESSION SUMMARY
Date: | 2026-01-26
Session: | OpenSCAD Chassis Design - Vision Test Platform
Duration: | ~2 hours
Focus: | CAD design, OpenSCAD fundamentals, parametric chassis creation
OVERVIEW
Pivoted from exploring existing Spot Micro designs to creating custom parametric OpenSCAD chassis optimized for vision testing. Compared Claude vs Gemini recommendations, verified claims about existing projects (Metabot, OpenCat), and made strategic decision to build purpose-built platform rather than adapt complex existing designs.
KEY ACCOMPLISHMENTS
1. Strategic Decision: Vision-First Approach
- Decided to build minimal test chassis before adding mobility
- Focus on camera mounting and vision algorithms first
- Defer wheel/leg mechanisms until vision system validated
2. Created camera_stereo_bar.scad (Parametric Camera Mount)
- 150mm baseline optimized for 2-400cm detection range
- Exact mounting for Camera Module 3 Wide (120° FOV)
- M2 camera mounting, M3 chassis mounting
- Cable routing channels integrated
- Fully parametric - adjust baseline with single variable
3. Created vision_test_chassis.scad (Complete Test Platform)
- 200×150mm footprint (Spot Micro compatible dimensions)
- 130mm height (cameras at 13cm - optimal for vision)
- Raspberry Pi 5 mounting with standoffs
- Anker PowerCore 20000 battery compartment
- Future Spot leg mounting holes pre-marked
- Weight reduction holes for efficiency
4. Research & Analysis: Compared AI Assistant Recommendations
- Evaluated Claude vs Gemini design approaches
- Verified Gemini's Metabot claim (TRUE - exists with OpenSCAD)
- Debunked "SpotMicro OpenSCAD" claim (FALSE - doesn't exist)
- Analyzed OpenCat (software framework, not CAD files)
5. Learned Critical CAD Workflow Distinctions
- STL import vs parametric design trade-offs
- When to adapt vs build from scratch
- Parametric code advantages over mesh editing
TECHNICAL DETAILS
Camera Configuration:
- Baseline: 150mm (optimal for 50-300cm depth perception)
- Module: Raspberry Pi Camera Module 3 Wide (120° FOV)
- Height: 130mm above ground (good horizon view)
- Mounting: M2 screws, 21mm hole spacing
Chassis Specifications:
- Dimensions: 200×150×130mm (L×W×H)
- Base plate: 3mm PLA
- Struts: 15mm square, 3mm wall thickness, hollow for weight savings
- Pi 5 standoffs: 8mm height for cooling
- Battery pocket: Recessed 1mm for retention
OpenSCAD Design Principles:
- All dimensions parameterized (easy to modify)
- $fn = 60 for preview, increase to 100 for final export
- No supports needed for printing
- Modular design (camera bar separate from chassis)
Print Settings (Prusa CORE One):
- Material: PLA
- Layer height: 0.15-0.2mm
- Infill: 20-30%
- Print time: ~4-6 hours (chassis), ~1 hour (camera bar)
FILES CREATED
1. camera_stereo_bar.scad
- Parametric stereo camera mounting bar
- 420 lines of documented OpenSCAD code
- Includes reference models for visualization
2. vision_test_chassis.scad
- Complete vision test platform
- 520 lines of documented OpenSCAD code
- Component references for Pi5 and battery
KEY DESIGN DECISIONS
Why Parametric from Scratch vs Adapting Existing:
✓ Faster iteration (2 sec preview vs minutes for STL)
✓ Exact fit for specific components (Pi5, Camera Module 3)
✓ Educational value (learn OpenSCAD properly)
✓ Lightweight files (~10KB vs 100MB STL)
✓ Version control friendly (text vs binary)
✗ No pre-validated leg geometry (can add later)
Why Vision-First Approach:
- Camera/vision is project core differentiator
- Can test algorithms on static platform
- Mobility can be added incrementally
- Reduces complexity during learning phase
Why 130mm Camera Height:
- Matches Spot Micro standing height (~13-15cm)
- Good balance of horizon view vs close obstacle detection
- Low enough for stable center of gravity
- High enough to avoid seeing mostly floor
Why 150mm Stereo Baseline:
- Optimal for 50-300cm range (sweet spot for indoor robot)
- Based on stereo vision formula: baseline ≈ 1/10 to 1/20 of max range
- 400cm max detection → 20-40mm baseline range
- 150mm chosen for good all-around performance
KEY LEARNINGS
OpenSCAD Workflow:
- Code-based CAD is ideal for version control and parametric design
- $fn variable controls curve smoothness (not dimensional accuracy)
- Clearances must be designed in (0.2-0.3mm for sliding fits)
- difference() for subtractive features (holes, pockets)
- Modules enable reusable, readable code
AI Assistant Comparison:
- Both can hallucinate, but in different ways
- Gemini initially hallucinated "SpotMicro OpenSCAD" existence
- Gemini correctly identified Metabot (verified via web search)
- Claude initially too dismissive of existing parametric projects
- Both converged on correct recommendation: custom build
Design Philosophy Insights:
- "Box-Dog" concept: simple platform beats premature complexity
- Parametric design pays off even for one-off parts
- Documentation in code is as important as code itself
- Design for current needs, plan for future expansion
NEXT STEPS
Immediate (Next Session):
1. Preview both .scad files in OpenSCAD
2. Verify Camera Module 3 dimensions match specs
3. Export STL files (F6 render, then Export)
4. Slice in PrusaSlicer
5. Print camera bar first (quick test, ~1 hour)
Short Term (1-2 weeks):
1. Print complete chassis
2. Assemble: Pi5 + battery + camera bar
3. Test camera mounting and cable routing
4. Begin stereo vision calibration